## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | PROJECT MANAGER
Handwritten digit recognition | Sean Costello
PROJECT DELIVERABLE | MNIST dataset, GUI, trained machine learning model, tech report, code on Github
SCOPE STATEMENT | this project focuses on developing a digit recognition using the MNIST dataset and a GUI. It also includes training the model.
START DATE | END DATE | OVERALL PROGRESS
2025-10-19 | 2025-10-28 | 100%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Set Kickoff Meeting | Sean C. | 2025-10-19 | 2025-10-19 | 1 | Complete | Project manager managed the team communication
Agree on Objectives | All | 2025-10-19 | 2025-10-19 | 1 | Complete
Detailed Requirements | All | 2025-10-22 | 2025-10-22 | 1 | Complete
Technical Requirements | All | 2025-10-22 | 2025-10-22 | 1 | Complete
Model | Sean C. | 2025-10-22 | 2025-10-24 | 2 | Complete
Model training | Sara S. | 2025-10-24 | 2025-10-24 | 1 | Complete
MNIST dataset | Sean C. | 2025-10-22 | 2025-10-24 | 2 | Complete
GUI | Eva M. | 2025-10-24 | 2025-10-28 | 4 | Complete
Testing | All | 2025-10-28 | 2025-10-28 | 1 | Complete
Development Complete | All | 2025-10-28 | 2025-10-28 | 1 | Complete
Tech report | Sara S. | 2025-10-19 | 2025-10-28 | 9 | Complete
System Testing | All | 2025-10-28 | 2025-10-28 | 1 | Complete